## Detailed Project Plan
Image matching and sales forcasting : Deep Learning
Week Start Date
|  |  | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | 2017-06-05 | 2017-06-12
Sl. no. | Stages | Tasks/Milestones | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
1 | Data Gathering & Pre-Processing | Product Image Collection, pre-processing
Sales data collection/creation
Sliders containing Solution Approach and UI Mockup ***
3 | Image Matching Engine | Exploring & documenting various Image Matching techniques using Deep Learning
Code prepartion for various algorithms
Comparison and Evaluation of the shortlisted techniques
Sumbmission of Final codes and and Excel File containing model parameters ***
Finalization of Engine & Sign off from Vineet
2 | Infrastructure Setup | Techical specifications for infrastructure setup.
Framework Finalisation
Installation and testing of Frameworks
Creation of installation document ***
4 | Sales Forecast Engine | Creation of sales forecasting equation
Integration of Image matching Engine & Sales Forecast Engine
Testing and evaluation of model parameters
Sign off from Vineet
5 | UI & Dashboard Creation | Mock up finalization ***
Setting up server and UI frameworks
Integration of Image processing Engine, Sales Forecast Engine and Front-End
Finalization of metrics and Dashboard creation ***
Sign-off from Vineet
* These timelines are based on 3 working resources |  |  |  | WIP
*** Milestones or Key Deliverables |  |  |  | Completed
Planned